## README
Sentosa CMS — FRD v0.5 vs. Current Build: Handover Checklist
Prepared for BA handover — comparing 'SDC IIS CMS FRD v0.5_SDC.pdf' against the current sts-bnk (Sentosa) source code.
Purpose
This workbook lists every feature/requirement in FRD v0.5 (85 pages, sections 1-16), grouped by CMS module, with a build-status verdict checked directly against the current source code (not against older internal planning docs, which may be out of date).
How to use it
- 'Feature Checklist' tab: one row per requirement. Use the Status dropdown (column F) to re-classify as you verify; conditional colour updates automatically. Tick column G once you've personally re-confirmed a row.
- 'Open Items - Need Shinfeng' tab: everything that cannot be marked Built/Not-Built until the BA (Wong Shin Feng) confirms intent — includes the FRD's own Section 15 'Open Items', blank tables in the FRD itself (3.3.4, Section 14), and material code/FRD contradictions found during this review.
- 'Summary' tab: auto-counted totals per module and overall, driven by formulas off the Feature Checklist tab.
Status legend
Built — implemented and verified in current code.
Partially Built — some part implemented; gap described in the Notes column.
Not Built — no implementation found after a repo-wide search.
Unclear / Needs BA Confirmation — cannot be verified because the FRD itself is silent/blank/ambiguous on this point.
Important caveats
- The codebase evolves quickly. Several older planning docs in the repo root (FSD_V0.5_ENHANCEMENT_PLAN.md dated 2026-07-06, INCIDENT_CATEGORY_IMPLEMENTATION_PLAN.md, etc.) are already partially superseded — this checklist verifies against the LIVE code as of 2026-07-16, not those docs.
- The live runtime datastore is MongoDB via src/lib/db.ts. prisma/schema.prisma is largely a documentation mirror and not always what's actually queried at runtime — evidence cites the live code wherever the two diverge.
- Several admin configuration areas (Users, Roles, Distribution Groups, Broadcast Config, Taxonomy) persist to browser localStorage rather than a shared server database — flagged individually in the checklist, and summarised as a cross-cutting open item.
Source: SDC IIS CMS FRD v0.5_SDC.pdf (Prepared by Wong Shin Feng, Business Analyst, SJ)
Prepared: 2026-07-16

## Summary
Sentosa CMS — Build Status Summary by Module
Module | Built | Partially Built | Not Built | N/A (by design) | Unclear / Needs BA | Total
1. CMS Overview & Dashboard | 5 | 4 | 9 | 0 | 0 | 18
2. UCS Integration | 0 | 1 | 7 | 0 | 0 | 8
3. User Roles & Permissions | 6 | 4 | 6 | 0 | 2 | 18
4. Case Data Model | 7 | 0 | 0 | 0 | 2 | 9
5. Incident Management | 29 | 6 | 6 | 0 | 0 | 41
6. Fault Reporting | 5 | 2 | 0 | 1 | 0 | 8
7. Task Management | 5 | 1 | 0 | 0 | 0 | 6
8. Events Master List | 12 | 1 | 0 | 0 | 1 | 14
9. e-Diary | 2 | 5 | 3 | 0 | 0 | 10
10. Broadcast & Notification | 5 | 5 | 14 | 0 | 3 | 27
11. Crisis Management & Emergency Recall | 2 | 0 | 9 | 0 | 0 | 11
12. Reporting & Data Export | 0 | 0 | 8 | 0 | 0 | 8
13. System Configuration & Administration | 11 | 8 | 12 | 0 | 1 | 32
14. Non-Functional Requirements | 1 | 0 | 1 | 0 | 5 | 7
TOTAL — All Modules | 90 | 37 | 75 | 1 | 14 | 217
Open items requiring Shinfeng (BA) confirmation: | 19
See 'Open Items - Need Shinfeng' tab for full detail.

## Feature Checklist
# | Module | Sub-Area / FRD Ref | Feature / Requirement | FRD Section | Status | Confirmed? | Evidence (Current Code) | Notes / Gap Description
1 | 1. CMS Overview & Dashboard | 2.1-2.2 Modules | CMS covers Incident/Fault/Task/NOP/Events/e-Diary/Distribution Group/Broadcast/Dashboard/Sys Config | 2.1-2.2 | Built | No | Matching route folders exist for all modules | Central Rostering is explicitly 'proposed' in FRD (15.4) — correctly not built
2 | 1. CMS Overview & Dashboard | 2.2 Modules | Crisis Recall as standalone module | 2.2 | Not Built | No | grep 'Crisis Recall' -> only a label in admin/roles matrix, no page/API/data model
3 | 1. CMS Overview & Dashboard | 2.3.1 Auth | WOG SSO authentication for SDC users | 2.3.1 | Not Built | No | RoleContext.tsx is a client-side role switcher via localStorage, no SSO/login flow | No real auth exists at all
4 | 1. CMS Overview & Dashboard | 2.3.1 Auth | Non-SSO username/password + 2FA | 2.3.1 | Not Built | No | No login form or password field anywhere in src/app
5 | 1. CMS Overview & Dashboard | 2.3.1 Auth | Deny access / redirect if no active CMS account or role | 2.3.1 | Not Built | No | No such gate; app loads straight into Dashboard
6 | 1. CMS Overview & Dashboard | 2.4.1 Navigation | Nav items: Dashboard, Case Mgmt, Incident, Fault, Task, Events, NOP, Broadcast, Statistics, Sys Config | 2.4.1 | Built | No | Sidebar.tsx NAV_GROUPS/ADMIN_ITEMS map 1:1 to real routes | Incident/Fault/Task are sub-tabs inside /case-management rather than top-level nav - functionally equivalent
7 | 1. CMS Overview & Dashboard | 2.4.1 Navigation | Nav items filtered by assigned role | 2.4.1 | Partially Built | No | Sidebar.tsx only gates the Administration section (role==='System Administrator'); Ops/Planning/Comms/Analytics items render for every role | Responder/Stakeholder should have narrower nav per FRD 3.1 role table
8 | 1. CMS Overview & Dashboard | 2.4.2 Summary Metrics | 9 dashboard counters: Active Cases, Incidents Reported, Unclosed Incidents, Faults Reported, Unclosed Faults, Active Tasks, Overdue Tasks, Events Today, Active NOPs | 2.4.2 | Built | No | src/app/page.tsx lines ~98-104, 60-64 | All 9 counters exist and compute correctly
9 | 1. CMS Overview & Dashboard | 2.4.2 Summary Metrics | Each metric filterable by date/time range | 2.4.2 | Partially Built | No | page.tsx lines 160-164 UI text itself says 'Affects: Incidents Reported, Faults Reported' only | Only 2 of 9 metrics respond to the date filter; FRD says 'each'
10 | 1. CMS Overview & Dashboard | 2.4.3-2.4.4 Map | Events Today metric + events surfaced on dashboard | 2.4.3 | Built | No | page.tsx lines 263-273
11 | 1. CMS Overview & Dashboard | 2.4.4 Map | Events shown as boundary/area overlays on 2D map | 2.4.4 | Partially Built | No | MapComponent.tsx updateEventMarkers plots point pins only; BoundaryMapDrawer polygon data (EventRecord.boundaryCoordinates) is captured but never rendered on the dashboard map
12 | 1. CMS Overview & Dashboard | 2.4.4 Map | 2D map of Sentosa using OneMap API | 2.4.4 | Not Built | No | MapComponent.tsx uses CartoDB/OpenStreetMap tiles; only a cosmetic label 'OneMap API Layout' exists in incidents/new/page.tsx | No real OneMap integration/geocoding anywhere in repo
13 | 1. CMS Overview & Dashboard | 2.4.4 Map | Incident pins geocoded from text address via OneMap | 2.4.4 | Partially Built | No | MapComponent.tsx plots directly from stored lat/lng; no geocoding API call exists | Manual pin-drop path works; auto-geocode path does not
14 | 1. CMS Overview & Dashboard | 2.4.4 Map | Faults shown as separate drop-pin map layer | 2.4.4 | Not Built | No | MapComponent has no 'faults' prop at all; dashboard fetches faults but never passes them to the map
15 | 1. CMS Overview & Dashboard | 2.4.4 Map | Active Works (NOP) boundary overlay layer | 2.4.4 | Not Built | No | No NOP-related code in MapComponent; BoundaryMapDrawer.tsx comment itself says NOP map integration is an unbuilt follow-on
16 | 1. CMS Overview & Dashboard | 2.4.4 Map | Pin clustering at zoom levels | 2.4.4 | Not Built | No | No clustering library wired in (grep 'markercluster' -> no matches)
17 | 1. CMS Overview & Dashboard | 2.4.4 Map | Pin click -> summary panel with link to full record | 2.4.4 | Built | No | MapComponent.tsx popupContent lines ~141-171
18 | 1. CMS Overview & Dashboard | 2.4.4 Map | Map coverage beyond Sentosa (Mt Faber/HarbourFront/VivoCity) | 2.4.4 | Not Built | No | MapComponent.tsx hardcodes maxBounds to Sentosa Island only (1.23-1.27 lat / 103.79-103.86 lng)
19 | 2. UCS Integration | 2.5.1 | Live metric feed to UCS Dashboard | 2.5.1 | Not Built | No | No /ucs route or feed export anywhere in src/app/api | 'UCS' only exists as a dropdown value for Incident reporting source
20 | 2. UCS Integration | 2.5.2 | Embedded CMS functions within UCS (inline CRUD widgets) | 2.5.2 | Not Built | No | No embeddable widget/iframe/API contract for UCS consumption
21 | 2. UCS Integration | 2.5.3 | Navigation from UCS to CMS record pages | 2.5.3 | Not Built | No | No UCS-side code in this repo to navigate from | Inherently a UCS-side feature; confirm UCS is tracked in a separate repo
22 | 2. UCS Integration | 2.5.4 | Incident creation from UCS, pre-populated from VA alert | 2.5.4 | Partially Built | No | Incident form supports 'UCS'/'VA' reporting-source tags + duplicate-check API exists | No actual UCS-side trigger/embed exists, only the CMS tagging field
23 | 2. UCS Integration | 2.5.5 | External weather alert forwarding -> advisory broadcast | 2.5.5 | Not Built | No | grep 'weather' -> only an incident sub-type label and a placeholder example string
24 | 2. UCS Integration | 2.5.6 | Last 10 Actions widget (CMS -> UCS) | 2.5.6 | Not Built | No | grep 'last 10 action' -> zero matches
25 | 2. UCS Integration | 2.5.7 | Broadcast integration with UCS | 2.5.7 | Not Built | No | Broadcast core exists in CMS but no UCS-facing surface or 'has draft broadcast' indicator
26 | 2. UCS Integration | 2.5.8 | Crisis Recall with UCS | 2.5.8 | Not Built | No | No Crisis Recall feature exists in CMS at all (see module 11)
27 | 3. User Roles & Permissions | 3.1 Roles | 11 named system roles (Sys Admin, Current Ops Admin, DM, DO, Controller, Responder, Stakeholder, Broadcast Recipient, Zone/Contract Mgr Non-IFM, OR Analyst, NOP Applicant/Approver) | 3.1 | Partially Built | No | RoleContext.tsx UserRole type only defines 7 switchable roles; 3 more exist as free-text strings in mock data (not selectable) | Zone/Contract Manager, NOP Applicant, NOP Approver roles are entirely missing from code
28 | 3. User Roles & Permissions | 3.1 Roles | Per-role system access matrix (view/edit/provisioning scope) | 3.1 | Built | No | admin/roles/page.tsx DEFAULT_ROLES/DEFAULT_MATRIX reproduces the FRD matrix closely | IMPORTANT: this matrix is display-only - no other page reads it; real gating is hardcoded booleans per-page, so editing this admin screen has no functional effect
29 | 3. User Roles & Permissions | 3.1 Roles | Current Ops Administrator gets Taxonomy management access (but not user/role provisioning) | 3.1 | Not Built | No | AdminGuard.tsx blocks ALL /admin/* pages incl. Taxonomy to non-'System Administrator' roles | Contradicts FRD row granting Current Ops Admin taxonomy management
30 | 3. User Roles & Permissions | 3.2 DM Elevation | DO (and per v0.5, Controller) elevation to DM permissions | 3.2 | Partially Built | No | Sidebar.tsx has a purely local, non-persisted 'isDOElevated' toggle only for Duty Officer role | Not tied to backend, lost on refresh, doesn't gate any actual permission; Controller elevation not implemented at all
31 | 3. User Roles & Permissions | 3.2 DM Elevation | Only Sys Admin/Current Ops Admin may grant elevation; shift start/end + grace period + granting admin recorded | 3.2 | Not Built | No | grep 'elevat' -> only the Sidebar toggle + static descriptive text in admin/roles and admin/users pages | No grant workflow, no data model for elevation records
32 | 3. User Roles & Permissions | 3.2 DM Elevation | Auto-revert after configurable grace period | 3.2 | Not Built | No | No grace-period timer/config found in admin/system-settings
33 | 3. User Roles & Permissions | 3.2 DM Elevation | Elevated user cannot close/endorse incident they created themselves | 3.2 / 5.10.1h | Not Built | No | incidents/[...id]/page.tsx allows endorsement action with no creator/submitter identity check | Same root gap as FRD 5.10.1(h)/(i) separation-of-duties rule
34 | 3. User Roles & Permissions | 3.3.1 Incident Matrix | Incident status lifecycle per role/status action matrix | 3.3.1 | Built | No | API knownActions + incident detail page action buttons implement full lifecycle gating by isCtrl/isMgr/isRanger | 'Live (Pending Controller Review)' modeled as a per-Responder lifecycleStatus, not an Incident-level status - a data-shape nuance, not a functional gap
35 | 3. User Roles & Permissions | 3.3.1 Incident Matrix | Duty Officer cannot self-submit for endorsement; can only endorse if elevated AND not the original submitter | 3.3.1 | Partially Built | No | isMgr treats Duty Officer identically to Duty Manager with no elevation-state or submitter-identity check | Any Duty Officer can approve/return endorsement at any time - no elevation gating, no self-endorsement block
36 | 3. User Roles & Permissions | 3.3.1 Incident Matrix | SDC Stakeholder: view-only, scoped to authorised/relevant incident records | 3.3.1 / 3.5 | Partially Built | No | No Stakeholder branch in incident page -> defaults to read-only (satisfies view-only) but not scoped by type/department | Stakeholder can view ALL incidents, not just relevant ones
37 | 3. User Roles & Permissions | 3.3.1 Incident Matrix | Closed incident stays viewable ~12 hours post-closure (Controller) | 3.3.1 | Unclear / Needs BA Confirmation | No | No 12-hour visibility window logic found; closed incidents remain visible indefinitely | Also unclear in FRD itself whether this means hide-after-12h or something else - needs BA clarification
38 | 3. User Roles & Permissions | 3.3.2 Task Matrix | Task status lifecycle + role actions (Controller/DM/DO broad rights, Assignee restricted, no access pre-assignment) | 3.3.2 | Built | No | tasks/[...id]/page.tsx + api/tasks/[...id]/route.ts role gating (isCtrl/isMgr/isRanger/isAssignee) | Code adds 2 extra statuses (Pending Closure, Returned) beyond FRD's 6-status table - functional enhancement, flag for FRD doc update
39 | 3. User Roles & Permissions | 3.3.3 e-Diary Matrix | Create/View limited to Sys Admin/Current Ops Admin/DM/DO/Controller only | 3.3.3 | Built | No | EDiaryTab.tsx ALLOWED_ROLES matches FRD list (plus Current Ops Admin)
40 | 3. User Roles & Permissions | 3.3.3 e-Diary Matrix | Edit: not allowed for any role (immutable after submission) | 3.3.3 | Built | No | api/occurrences/route.ts has only GET/POST handlers, no PATCH | NOTE: this actually conflicts with FRD 9.1(c) which wants entries mutable w/ tracked amendments - see e-Diary module
41 | 3. User Roles & Permissions | 3.3.3 e-Diary Matrix | Delete: allowed for System Administrator only | 3.3.3 | Not Built | No | No DELETE handler exists in api/occurrences/route.ts at all - even Sys Admin cannot delete
42 | 3. User Roles & Permissions | 3.3.4 Events Matrix | Role/status action matrix for Events Management | 3.3.4 | Unclear / Needs BA Confirmation | No | FRD source PDF page 31: heading '3.3.4 Events Management' appears with NO table beneath it, jumps straight to 3.4 | FRD authoring gap, not a code gap. EventsTab.tsx uses a placeholder role list pending confirmation. NEEDS SHINFENG INPUT.
43 | 3. User Roles & Permissions | 3.4 Data Retention | Deactivated user's records remain accessible; creator identity preserved | 3.4 | Built | No | Records store createdBy as plain string (no FK), so deactivation cannot cascade-delete/orphan attribution | Caveat: entire user system is mock/localStorage, not a real backend - retention is a side-effect, not an engineered feature
44 | 3. User Roles & Permissions | 3.5 Stakeholder Access | SDC Stakeholder auto-granted view-only access scoped by Incident Type | 3.5 | Not Built | No | grep 'Stakeholder' in api/incidents -> no matches; no type/department scoping logic exists | Stakeholder sees all incidents by default, not scoped subset
45 | 4. Case Data Model | 4.1-4.2 | Case as lean parent: 0/1 Incident, 0..n Tasks, 0..n CMMS Fault tickets, 0..n e-Diary entries | 4.1-4.2 | Built | No | src/lib/db.ts Case interface: incident, cmmsTickets[], taskCount/occurrenceCount/faultCount
46 | 4. Case Data Model | 4.2 | Master/Slave (duplicate) incident linkage | 4.2 | Built | No | db.ts SlaveIncident interface, isDuplicate/masterIncidentId fields, link-duplicate action
47 | 4. Case Data Model | 4.1(f) | Auto-create Case when Incident/Task created without existing Case | 4.1 | Built | No | api/cases/route.ts generateCaseId + generateIncidentId in one POST
48 | 4. Case Data Model | 4.1(g) | Auto-create Case when e-Diary entry created without existing Case | 4.1 | Unclear / Needs BA Confirmation | No | Occurrence.caseId is optional in db.ts, suggesting entries can exist without a Case | Needs follow-up read of api/occurrences/route.ts POST handler to confirm/deny auto-case-creation
49 | 4. Case Data Model | 4.1(h) | Events are NOT Case sub-records; don't affect Case status | 4.1 | Built | No | EventRecord has no caseId field at all, only optional sourceEDiaryId
50 | 4. Case Data Model | 4.3.1 | Case ID format SEN/CI/YYYYMMDD/NNN | 4.3.1 | Built | No | db.ts generateCaseId()
51 | 4. Case Data Model | 4.3.1 | Case fields: ID/Title/Status/CreatedBy-At/ClosedBy-At (system managed) | 4.3.1 | Built | No | Case interface fields match 1:1 | Title auto-population for VA/system-triggered vs Controller-input not independently re-verified
52 | 4. Case Data Model | 4.3.2 | Case statuses Pending Triage -> Active/No Action Required -> Closed with defined transition rules | 4.3.2 | Built | No | api/cases/[...id]/route.ts explicit allow-list + auto-transition to Active on child record add
53 | 4. Case Data Model | 4.3.2 | Controller may close Case after CMMS ticket raised, without waiting for IFM resolution | 4.3.2 | Unclear / Needs BA Confirmation | No | Not specifically isolated in this pass | Recommend a follow-up check of the Case-closure validation branch
54 | 5. Incident Management | 5.1.1 Types | Type + Sub-type mandatory, unique sub-types per type, 'Others' fallback | 5.1.1 | Built | No | src/lib/taxonomy.ts DEFAULT_REFERENCE_DATA + validation in api/cases/route.ts | 'Others' fallback not present as a seeded default option
55 | 5. Incident Management | 5.1.2 Categories | 3 categories (Operational/Backdated/Informational-Exercise) drive default response/assignment/closure/broadcast behaviour | 5.1.2 | Built | No | src/lib/incidentCategory.ts, wired into create + update routes | All 3 categories currently share identical lifecycle; only behavioural diff is optional Responder assignment (already true for all) - confirm this satisfies FRD intent
56 | 5. Incident Management | 5.2 Crisis Level | Default Level 4 at creation; Controller/DM/DO can escalate; 45-min reminder | 5.2 | Built | No | api/cases/route.ts crisisReminderDue = +45min; incident page fires notification at elapsed 45min | Reminder is client-side only - fires only while someone has that incident's page open, no server cron/push
57 | 5. Incident Management | 5.3.1 General Info | ID/Case ID auto-format, Title, DateTime, Type/Subtype, Priority, Crisis Level, Reporter, Requested/Created By, Status, Assigned To | 5.3.1 | Built | No | ID format SEN/IR/YYYYMMDD/NNNN in db.ts; all fields present in incidents/new/page.tsx
58 | 5. Incident Management | 5.3.2 Location | Road/Building/Level+Space/Near-At/Common Name/Postal Code(default 000000)/Tags/mini-map pin drop | 5.3.2 | Built | No | LocationSelector.tsx + incidents/new/page.tsx | Minimap is a static/mock 'OneMap API Layout' placeholder, not a live GIS integration
59 | 5. Incident Management | 5.3.3 Incident Log | Event Number auto, timestamped Date/Time/Description rows, auto-sorted | 5.3.3 | Built | No | api/incidents/[...id]/route.ts makeLogEntry(), timeline rendering in incident detail page
60 | 5. Incident Management | 5.3.4 Emergency Services | Police / Ambulance / SCDF fields | 5.3.4 | Built | No | EmergencyService model + incident detail page panels
61 | 5. Incident Management | 5.3.5 Media Involvement | Media at Scene flag, Media Name, SDC Comms notification prompt | 5.3.5 | Built | No | api/incidents/[...id]/route.ts auto-logs media presence + comms-notified entries
62 | 5. Incident Management | 5.3.6 Property/Vehicles | SDC property damage + description; vehicle fields | 5.3.6 | Built | No | PropertyDamage / VehicleInvolved models + incident detail accordion
63 | 5. Incident Management | 5.3.7 Persons Involved | Guest/Non-guest, Type, Name, Address, Age, Gender, Contact, Role, Injury flag | 5.3.7 | Built | No | PersonInvolved model + incident detail accordion
64 | 5. Incident Management | 5.3.8 Personal Injuries | Clinic/Hospital, MSIG form+serial, Under-16 + guardian sub-form | 5.3.8 | Built | No | PersonalInjury model incl. under16/parentGuardianName/Contact
65 | 5. Incident Management | 5.3.9 CCTV/BWC | Camera No, VMS timestamp/bookmark, BWC No/timestamp, multi-entry | 5.3.9 | Built | No | incident detail page CCTV & BWC accordion, multi-entry array
66 | 5. Incident Management | 5.3.10 Attachments | File upload (photo/video/doc), police reports excluded | 5.3.10 | Built | No | incident detail Attachments accordion | No hard filter blocking 'police report' file types - relies on user discipline; confirm if a hard rule is required
67 | 5. Incident Management | 5.3.11 Summary/Closure | Summary text, Endorsement history, mandatory Return remarks, Closed By/At, Closure Broadcast status | 5.3.11 | Partially Built | No | Summary autosave + closedBy/At + return-remarks-required logic all built; broadcast status badge shown | No dedicated role-gated 'Endorsement Submission History' panel - only generic timeline log entries
68 | 5. Incident Management | 5.4 Lifecycle | Manual/auto creation, auto Case creation, optional Responder, Closed = read-only, Sys-Admin-only reopen | 5.4 | Built | No | api/cases/route.ts + api/incidents/[...id]/route.ts reopen action gated to System Administrator
69 | 5. Incident Management | 5.4.1 Status Defs | 9 official v0.5 statuses incl. new 'Pending Controller Review' | 5.4.1 | Partially Built | No | Incident-level status covers 5 values; per-Responder lifecycleStatus covers the other 4 (Ack/OnSite/PendingCtrlReview/Incomplete/Completed) | Intentional Incident/Responder status-split architecture (see Incident_Status_Model_Design_Updated.docx) - captures same info but FRD's single-status-column model no longer matches 1:1; flag for FRD wording update, not a functional gap
70 | 5. Incident Management | 5.4.2 Process Flow | High-level incident process flow (Fig 5-1/5-2) | 5.4.2 | Built | No | incidents/lifecycle/page.tsx renders an interactive lifecycle reference page
71 | 5. Incident Management | 5.4.3 Ageing Alerts | 12-day notice, 14-day escalation | 5.4.3 | Partially Built | No | incident detail page fires client-side notifications at 12/14 days elapsed | Fires only while that incident's own page is open in-browser, not a server-side push
72 | 5. Incident Management | 5.4.3 Ageing Alerts | Daily Ageing Summary report, 30 min after shift start, to Duty Manager | 5.4.3 | Not Built | No | No cron/scheduled job or summary report page found (searched 'ageing summary','shift start')
73 | 5. Incident Management | 5.4.4 Reporting Sources | Source field on Incident (Public/Email/UCS/VA/State Agency etc.) | 5.4.4 | Built | No | incident.reportingSource field + dropdown + filter in IncidentLogTab.tsx
74 | 5. Incident Management | 5.5.1 Assignment | Multi-Responder assign, assign anytime while Live, notify on assignment, reassignment allowed | 5.5.1 | Built | No | api/incidents/[...id]/route.ts assign action + MultiResponderSelect.tsx | Notification is in-app only (NotificationContext) - no SMS/email dispatch confirmed
75 | 5. Incident Management | 5.5.2 Milestone Tracking | Dispatch/Acknowledgement/Arrival/Activity/Completion per-Responder | 5.5.2 | Built | No | acknowledge/on-site/notify-complete actions update per-Responder lifecycleStatus + timestamps
76 | 5. Incident Management | 5.5.3 Incident Logging | Log editable across active statuses; view-only in Pending Endorsement/Closed; re-enabled on Return | 5.5.3 | Built | No | incident detail page edit/delete gated on status !== Pending Endorsement/Closed
77 | 5. Incident Management | 5.5.3(h) | Responder retains read-only access for 12 hours post-closure, then loses visibility | 5.5.3 | Not Built | No | No time-boxed visibility restriction found anywhere in app/context/lib | Needs an RBAC rule tied to a rolling 12h timer since closedAt; needs BA confirmation on exact enforcement wanted
78 | 5. Incident Management | 5.6 Duplicate Detection | Flag matching date/type/subtype; Controller override/proceed/link; linked duplicate closes with master | 5.6 | Built | No | api/incidents/check-duplicates (2-hour window) + link-duplicate action + close cascades slaveIncidents | Match window is a fixed +/-2 hours - an implementation assumption not specified by FRD; confirm with BA
79 | 5. Incident Management | 5.7.1 Save Mechanism | Auto-save at intervals, manual save, unsaved indicator, admin-configurable interval | 5.7.1 | Partially Built | No | incident page autosaves on a timer reading admin system-settings interval; unsaved indicator shown | Auto-save currently only flushes the Summary field, not a full-form periodic autosave of every section
80 | 5. Incident Management | 5.7.2 Concurrent Editing | Notify 2nd user record is being edited; conflict resolution on simultaneous save | 5.7.2 | Not Built | No | db.ts has editingBy/editingStartedAt fields defined but zero reads/writes anywhere in src | Schema placeholder only - no lock-acquire/release logic, no 'being edited by X' UI, no conflict prompt
81 | 5. Incident Management | 5.8 Linked Fault Creation | Raise Fault from active Incident, linked to CMMS workflow, independent closure | 5.8 | Built | No | incident detail page renders FaultCreateModal with linkedIncidentId; Fault stores linkedIncidentId
82 | 5. Incident Management | 5.9 False Alarm | Log + mark false alarm, no DM endorsement required, retained for audit | 5.9 | Built | No | api/incidents/[...id]/route.ts mark-false-alarm action sets Closed directly, isFalseAlarm=true
83 | 5. Incident Management | 5.10 Closure/Reopening | DM approval required (except false alarm); submit->review->approve/return; Closed=read-only; Sys-Admin-only reopen; closure broadcast prompt | 5.10 | Built | No | close/return/reopen actions in api/incidents/[...id]/route.ts implement full flow
84 | 5. Incident Management | 5.10.1(a) Endorsement Rules | Controller may submit/resubmit from any active status | 5.10.1 | Built | No | route.ts allows submit from Live/Live(Assigned)/Returned | 'Any active status' is narrower in code (3 statuses) but these are effectively all non-terminal Controller-facing statuses in the current model
85 | 5. Incident Management | 5.10.1(b) | Submission allowed even with incomplete Responder actions | 5.10.1 | Built | No | route.ts computes notYetReviewed but does not block submission outright
86 | 5. Incident Management | 5.10.1(c) | Alert Controller to incomplete Responder actions before accepting submission | 5.10.1 | Built | No | route.ts returns 409 with requiresForce + outstandingResponders list
87 | 5. Incident Management | 5.10.1(d) | Force-proceed requires confirmation + MANDATORY override remark | 5.10.1 | Partially Built | No | route.ts requires body.force=true boolean to bypass warning | No evidence a free-text override remark is actually captured/required - only a boolean confirm; log entry is auto-generated system text, not user-entered
88 | 5. Incident Management | 5.10.1(e) | Accepted submission sets status to Pending Endorsement | 5.10.1 | Built | No | route.ts
89 | 5. Incident Management | 5.10.1(f) | No recall/cancel of submission; amend only after Return | 5.10.1 | Built | No | No recall/cancel action exists in knownActions list
90 | 5. Incident Management | 5.10.1(g) | DM return -> Returned status; Controller can amend/update/manage responders/return-to-responder/resubmit | 5.10.1 | Built | No | return + return-to-responder actions + field-update endpoints remain callable while Returned
91 | 5. Incident Management | 5.10.1(h) | BLOCK DM endorsement where endorsing user = creator/submitter/resubmitter (separation of duties) | 5.10.1 | Not Built | No | Searched close action + whole codebase for 'separation'/actor-identity checks - none exist | HIGH PRIORITY GAP - compliance-relevant control completely unenforced at API and UI layers
92 | 5. Incident Management | 5.10.1(i) | Separation-of-duties rule applies even when using elevated DM permissions | 5.10.1 | Not Built | No | Depends entirely on (h) being built first - neither exists
93 | 5. Incident Management | 5.11.1 Closure Broadcast | Auto-trigger on DM endorsement; Controller reviews/confirms recipients/dispatches; one broadcast per incident; status+ID displayed | 5.11.1 | Partially Built | No | close action auto-creates a BroadcastLog entry (status PENDING) with templated content; status badge shown read-only | No Controller-facing review/confirm/dispatch UI exists at all - /broadcasts page is a literal 'Coming soon' stub, no /api/broadcasts route; broadcast permanently stuck at PENDING
94 | 5. Incident Management | 5.11.2 EOD Interim Broadcast | Flag open incidents for EOD batch queue; DM reviews/approves dispatch per incident | 5.11.2 | Not Built | No | admin/broadcast-config has an EOD template configured but no batch-queue mechanism, cron, or review screen found
95 | 6. Fault Reporting | 6.1 Entry Points | From active Incident, Standalone Case, SDC Staff App | 6.1 | Partially Built | No | FaultCreateModal supports linked-Incident and standalone/auto-create-case flows | No Staff-App-originated fault ingestion endpoint exists; likely out of CMS's direct control per FRD wording but confirm no webhook stub expected
96 | 6. Fault Reporting | 6.2.1 CMMS Ticket Creation | Check/auto-create Case; CMMS returns Ticket ID; CMMS manages status independently | 6.2.1 | Built | No | api/faults/route.ts auto-create Case; api/faults/[...id]/route.ts submit action calls /api/cmms-mock
97 | 6. Fault Reporting | 6.2.2 Fault Field Design | Field ID SEN/FR/YYYYMMDD/NNN, Case ID, Type/Subtype, Location, Description, Attachments, Created/Submitted/Closed By-At, Ticket ID | 6.2.2 | Built | No | generateFaultId() format matches; all fields present in Fault schema + FaultCreateModal | FRD note about Closed-By referencing DO/DM on Case closure vs code's literal 'system' string is an FRD-internal inconsistency (6.2.2 note vs 6.3.1 body) - flag for BA, not a code bug
98 | 6. Fault Reporting | 6.2.3 Process Flow | High-level CMMS ticket process flow (Fig 6-1) | 6.2.3 | Built | No | Implemented via submit action in api/faults/[...id]/route.ts
99 | 6. Fault Reporting | 6.3.1 Fault Status | Pending Submission (Controller) -> Closed (auto on CMMS ID receipt) | 6.3.1 | Built | No | Fault.status transitions exactly as FRD's 2-status table describes
100 | 6. Fault Reporting | 6.3 Retrieval | CMS retrieves live ticket status from CMMS API, surfaced on Case record | 6.3 | Partially Built | No | cmms-mock GET endpoint supports ticket lookup by ticketId | Not confirmed whether Fault/Case detail view re-queries CMMS for latest status after initial submission vs only at submission time - needs follow-up check
101 | 6. Fault Reporting | 6.4 Non-IFM Faults | Non-IFM faults continue in legacy system, not logged in CMS | 6.4 | N/A (excluded by design) | No | No code handles non-IFM fault categories, consistent with FRD's own scope exclusion | Correctly excluded - not a gap, confirms no accidental scope creep
102 | 6. Fault Reporting | 6.5 Case Linkage/Closure | CMMS Fault ID stored on Case; Fault auto-closes independent of CMMS ticket lifecycle; Case can close before CMMS resolves; multiple Fault IDs per Case | 6.5 | Built | No | Case.cmmsTickets[] array + src/lib/autoclose.ts treats ticket receipt as satisfied, never blocks closure
103 | 7. Task Management | 7.1.1 Creation | Created by Controller+, linked to Case, recurring + group assignment | 7.1.1 | Built | No | api/tasks/route.ts POST + src/lib/recurrence.ts + src/lib/seriesEngine.ts
104 | 7. Task Management | 7.1.2 Field Design | Task ID SEN/TA/YYYYMMDD/NNN, Linked Case ID, Title, Description, Assignee, Priority, Due Date, Checklist, Recurrence, Comments, Close Reason, Attachments, Created By/Date | 7.1.2 | Built | No | generateTaskId() + all fields in Task type + api/tasks/route.ts | Checklist gating (all items ticked before completion) enforced server-side
105 | 7. Task Management | 7.2 Assignment/Notification | Notify on assignment; reassignment resets to Assigned + notifies; individual or group assignment; Sys-Admin-configurable groups | 7.2 | Built | No | TaskBoardTab.tsx addNotification + api/tasks/[...id]/route.ts assign/reassign + src/lib/groups.ts | Notification is in-app only, not SMS/email/push
106 | 7. Task Management | 7.3.1 Process Requirements | Controller visibility of all statuses; Case can't auto-close with open Tasks; mandatory Close Reason if closed incomplete | 7.3.1 | Built | No | src/lib/autoclose.ts blocks Case auto-close on open tasks; close action requires closeReason when !completed
107 | 7. Task Management | 7.3.2 Task Statuses | 6 statuses: Created/Assigned/Acknowledged/In Progress/Pending Further Action/Closed, with permitted actions per role | 7.3.2 | Partially Built | No | All 6 FRD statuses implemented with full role-gated action switch | Code adds 2 extra states not in FRD's literal table: 'Pending Closure' (awaiting Controller accept/reject) and 'Returned' - mirrors Incident endorsement pattern; flag for FRD doc update or BA confirmation this enhancement is approved
108 | 7. Task Management | 7.3.3 Process Flow | High-level task process flow incl. Accept/Reject (Fig 7-1) | 7.3.3 | Built | No | Matches the Accept/Reject flow noted above per code's own comments referencing 'Fig 7-1' | Recommend BA re-check Figure 7-1 in the source PDF directly to confirm Pending Closure/Returned are meant to be there
109 | 8. Events Master List | 8.1.1 Requirements | Create/edit/manage Event records | 8.1.1 | Built | No | api/events/route.ts + api/events/[...id]/route.ts + EventCreateModal.tsx (full CRUD incl. delete)
110 | 8. Events Master List | 8.1.1 Requirements | Create Event from e-Diary entry, retain source reference | 8.1.1 | Built | No | EDiaryTab.tsx 'Create or Link Event' modal passes sourceEDiaryId into EventCreateModal
111 | 8. Events Master List | 8.1.1 Requirements | Events don't affect Case status/closure | 8.1.1 | Built | No | EventRecord has no caseId field at all | Confirmed deliberate per code comment referencing prior BA Q&A doc
112 | 8. Events Master List | 8.1.2 Field Design | Event ID, Name, Date/Time, Location, Type, Description, Linked e-Diary, Created By/At | 8.1.2 | Built | No | EventRecord interface + EventCreateModal.tsx form
113 | 8. Events Master List | 8.1.2 / 3.3.4 | Role gating for who can create/edit/delete Events | 8.1.2 | Unclear / Needs BA Confirmation | No | EventsTab.tsx code comment explicitly notes FRD 3.3.4 Events role matrix is blank | Same underlying FRD gap as row in Roles module - needs Shinfeng sign-off
114 | 8. Events Master List | 8.2 Event Location | Location selected from hierarchy (not free text) | 8.2 | Built | No | EventCreateModal.tsx uses LocationSelector; server requires location.commonName/road/building | Server-side validation is best-effort, relies on client-supplied hierarchy data
115 | 8. Events Master List | 8.2 Event Location | Draw event boundary on 2D map within selected hierarchy area, prevented outside area | 8.2 | Built | No | BoundaryMapDrawer.tsx radius-constrained boundary with explicit out-of-area error
116 | 8. Events Master List | 8.2 Event Location | Admin maintains location hierarchy, reference points, map-drawing rules | 8.2 | Built | No | admin/location-hierarchy/page.tsx CRUD
117 | 8. Events Master List | 8.3 Schedule Upload | Upload event schedule file (CSV/XLSX) | 8.3 | Built | No | EventScheduleUploadModal.tsx supports .csv/.xlsx via papaparse/xlsx libs
118 | 8. Events Master List | 8.3 Schedule Upload | Extract & present rows for review/amendment before import | 8.3 | Built | No | EventScheduleUploadModal.tsx step='review' editable table
119 | 8. Events Master List | 8.3 Schedule Upload | Validate Location against hierarchy; flag missing/incorrect/duplicate rows | 8.3 | Built | No | validateRows() flags missing fields, taxonomy mismatch, duplicates | Duplicate detection is intra-batch only, not against existing Events Master List records - minor gap
120 | 8. Events Master List | 8.3 Schedule Upload | Block confirm-import until all flags resolved; report success/failure per row | 8.3 | Built | No | Confirm button disabled while flaggedCount>0; per-row success/fail tracking on import
121 | 8. Events Master List | 8.4 Calendar/List View | Calendar view of events by date | 8.4 | Partially Built | No | EventTimelineView.tsx implements a single-day hourly agenda (prev/next day nav) | Satisfies 'view by date' but is a day-agenda view, not a month-grid calendar - confirm with BA if this meets intent
122 | 8. Events Master List | 8.4 Calendar/List View | List view filterable by date range and event type | 8.4 | Built | No | EventsTab.tsx Date From/To + Event Type filter + free-text search
123 | 9. e-Diary | 9.1(a) Creation Access | Limited to Controller/Duty Officer/Duty Manager/Sys Admin | 9.1 | Partially Built | No | EDiaryTab.tsx ALLOWED_ROLES includes 'Current Ops Administrator' in addition to the 4 FRD-listed roles | Not FRD-confirmed 5th role
124 | 9. e-Diary | 9.1(b) Creation | No approval/assignment workflow required | 9.1 | Built | No | api/occurrences/route.ts POST creates entry immediately, no approval step
125 | 9. e-Diary | 9.1(c) Mutability | Entries editable after submission (mutable); amendments tracked/timestamped; deletable only by Sys Admin | 9.1 | Not Built | No | api/occurrences/route.ts explicit code comment: 'No PATCH/DELETE endpoint by design... entry is immutable once submitted' | DIRECT CONTRADICTION with FRD 9.1(c). Prisma schema even models an unused EDiaryAmendment table. NEEDS URGENT BA CLARIFICATION - functional gap, not just doc lag
126 | 9. e-Diary | 9.1(d) Attachments | File/image attachments supported on e-Diary entries | 9.1 | Not Built | No | Occurrence.attachments field exists but always set to [] in POST; no upload UI in EDiaryTab create form
127 | 9. e-Diary | 9.1.2 Field Design | ID, Case ID (auto-create), Linked Incidents/Tasks/Events, Created By, backdatable Date/Time, Topic, Entry Text, Attachments | 9.1.2 | Partially Built | No | ID gen + auto-case-create + backdating + Topic/Content all present | Linked Tasks reference and Attachments are not implemented (only Linked Events and Linked Incidents via escalate flow exist)
128 | 9. e-Diary | 9.1.3(a) Create/Link | Create/link Incident, Task, OR Event from an e-Diary entry | 9.1.3 | Partially Built | No | 'Escalate to Incident' and 'Create or Link Event' both built in EDiaryTab.tsx | No equivalent 'Create/Link Task' action exists anywhere - FRD explicitly lists Task alongside Incident/Event
129 | 9. e-Diary | 9.1.3(b) Create/Link | New Incident/Task created in same Case, retains e-Diary reference | 9.1.3 | Partially Built | No | Incident path confirmed (passes caseId + fromEDiary params); Task path doesn't exist to evaluate
130 | 9. e-Diary | 9.1.3(c-e) | Event retains e-Diary reference; e-Diary entry itself unchanged after linking | 9.1.3 | Built | No | Linking only mutates EventRecord.sourceEDiaryId via PATCH; Occurrence record never touched
131 | 9. e-Diary | 9.2 Retrieval/Filtering | Filter by date AND by user account | 9.2 | Partially Built | No | api/occurrences/route.ts GET supports dateStart/dateEnd/user/topic server-side | EDiaryTab.tsx UI only exposes Date From/To, Topic, free-text search - no 'filter by user' control in the UI despite API support
132 | 9. e-Diary | 9.3 UCS Integration | e-Diary accessible as a UCS module | 9.3 | Not Built | No | No UCS integration code anywhere in repo | Explicitly defined within the separate UCS FRD per this FRD's own wording - flag as N/A for this codebase, confirm UCS-side delivery separately
133 | 10. Broadcast & Notification | 10.1 Closure Broadcast | Triggered on DM approval; Controller composes/confirms before dispatch | 10.1 | Partially Built | No | close action auto-creates BroadcastRecord (status PENDING); badge display exists | No code path anywhere sets status to 'dispatched' - no Controller-facing compose/confirm/dispatch UI exists at all
134 | 10. Broadcast & Notification | 10.1 EOD Broadcast | EOD Interim Broadcast - DM review queue | 10.1 | Not Built | No | No queue/review UI anywhere; only a static template category string in admin/broadcast-config
135 | 10. Broadcast & Notification | 10.1 Weather Broadcast | Weather Advisory Broadcast | 10.1 | Not Built | No | No weather-alert-triggered broadcast feature found
136 | 10. Broadcast & Notification | 10.1(a-e) | Broadcasts sent via email; prompts/templates/recipients scoped by type+crisis level | 10.1 | Not Built | No | No email-sending integration anywhere (no SMTP/nodemailer); BroadcastRecord.recipients hardcoded [] | Config exists in admin UI but never consumed since no dispatch flow exists
137 | 10. Broadcast & Notification | 10.2 Delivery Channels | Email channel for closure/EOD broadcasts | 10.2 | Not Built | No | No email gateway integration; only a mock config string 'smtp.sdc.gov.sg'
138 | 10. Broadcast & Notification | 10.2 Delivery Channels | Push notification for system notifications/prompts | 10.2 | Partially Built | No | In-app notification bell (NotificationContext/NotificationWidget) works | LocalStorage-only, single-browser-session, not a real push/WebSocket delivery despite a 'Real-time WebSocket Broadcast Server' being described as a mock config item
139 | 10. Broadcast & Notification | 10.3 Recipient Group | Named distribution groups, admin CRUD | 10.3 | Built | No | src/lib/groups.ts + admin/distribution-groups/page.tsx full CRUD incl. deactivate + audit log | Persisted in browser localStorage, not server DB - flag for BA/tech lead re multi-user deployment
140 | 10. Broadcast & Notification | 10.3 Recipient Group | Pre-populate recipients by incident type/crisis level at broadcast initiation | 10.3 | Not Built | No | No dispatch flow exists to exercise this; BroadcastRecord.recipients always []
141 | 10. Broadcast & Notification | 10.3 Recipient Group | DM/Controller can add/remove recipients pre-dispatch without altering group config | 10.3 | Not Built | No | No dispatch UI exists
142 | 10. Broadcast & Notification | 10.4 Broadcast Templates | Configurable templates mapped to incident type/crisis level | 10.4 | Built (config only, not consumed) | No | admin/broadcast-config/page.tsx Templates tab, CRUD with preview + variable substitution | Config UI exists but never actually applied at dispatch time
143 | 10. Broadcast & Notification | 10.4 Broadcast Templates | Default templates exclude sensitive content; explicit confirmation to include more | 10.4 | Not Built | No | No such logic found | FRD itself flags this content as 'to be confirmed' (see Open Items 15.3)
144 | 10. Broadcast & Notification | 10.5 System Notifications | Task assigned/reassigned -> Assignee | 10.5 | Built | No | addNotification() calls in cases/[...id]/page.tsx, TaskBoardTab.tsx, tasks/[...id]/page.tsx
145 | 10. Broadcast & Notification | 10.5 System Notifications | Incident assigned -> Responder notified | 10.5 | Unclear / Needs BA Confirmation | No | No explicit addNotification call tied to Responder assignment found; only static seed/mock data simulates this
146 | 10. Broadcast & Notification | 10.5 System Notifications | Responder marks complete -> Controller notified | 10.5 | Not Built | No | No addNotification call found for the notify-complete action
147 | 10. Broadcast & Notification | 10.5 System Notifications | Controller returns Responder input for amendment -> Responder notified | 10.5 | Not Built | No | No corresponding addNotification call found
148 | 10. Broadcast & Notification | 10.5 System Notifications | Incident log returned for revision by DM -> Controller notified | 10.5 | Not Built | No | 'return' action exists but no addNotification call accompanies it
149 | 10. Broadcast & Notification | 10.5 System Notifications | NOP status change -> Applicant/approvers notified | 10.5 | Unclear / Needs BA Confirmation | No | Only present as static seed data; NOP module live-wiring not verified in this pass
150 | 10. Broadcast & Notification | 10.5 System Notifications | CMMS Fault ID received -> Controller notified | 10.5 | Not Built | No | Only static seed data; no live trigger found in fault-linking code
151 | 10. Broadcast & Notification | 10.5 System Notifications | Incident active 12/14 days -> Duty Team ageing alerts | 10.5 | Partially Built | No | Real client-side computed alerts fire to DM/Controller/DO roles via addNotification | Only fires while a user has that specific incident's page open in-browser - no server-side scheduled job
152 | 10. Broadcast & Notification | 10.5 System Notifications | Incident closed -> closure broadcast prompt to Controller | 10.5 | Not Built | No | No addNotification call tied to closureBroadcastStatus==='pending'
153 | 10. Broadcast & Notification | 10.6 Broadcast Matrix | Full broadcast routing matrix (type/crisis level -> group/channel) | 10.6 | Unclear / Needs BA Confirmation | No | FRD itself states '[TBC - Full broadcast matrix]' | Open item in the FRD itself, not a code gap - a DEFAULT_MATRIX placeholder exists in admin config but is unconfirmed against real requirements
154 | 10. Broadcast & Notification | 10.7 EOD Interim Broadcast | Queue of open incidents flagged; DM reviews per-incident; selects template/confirms dispatch | 10.7 | Not Built | No | No such queue/workflow found anywhere
155 | 10. Broadcast & Notification | 10.8 SDC Comms Team Notification | Media confirmed -> prompt DM -> assign Controller -> Controller confirms notification made | 10.8 | Built | No | incident detail page 'Press/Media present' checkbox triggers a Communications Action banner + confirmation checkbox, logged to incident log | Simplified vs FRD - no explicit 'DM assigns a Controller' step, any user with edit rights can tick the box
156 | 10. Broadcast & Notification | 10.9 Broadcast Record/Export | Broadcasts logged against Case, identified by Broadcast ID | 10.9 | Built | No | BroadcastRecord.id format [CaseID]-BC[seq] | Only Closure Broadcast type is ever actually created; EOD/Weather never populate this
157 | 10. Broadcast & Notification | 10.9 Broadcast Record/Export | Record includes recipients/template/content/date-time/sending Controller/status | 10.9 | Partially Built | No | BroadcastRecord interface has all fields, populated at creation | recipients always [], sentAt/status never progress past null/PENDING since dispatch never happens
158 | 10. Broadcast & Notification | 10.9 Broadcast Record/Export | Incident shows Broadcast sent status | 10.9 | Partially Built | No | closureBroadcastStatus badge shown in incident detail | Perpetually stuck at 'Pending'
159 | 10. Broadcast & Notification | 10.9 Broadcast Record/Export | Delivery counts (sent/delivered/failed/pending) and ack counts | 10.9 | Not Built | No | BroadcastRecord.deliveryAttempts field exists but nothing increments it | No delivery-channel integration to report real counts
160 | 11. Crisis Management & Emergency Recall | 11.1 Crisis Level | Incident assigned crisis level 1-5 | 11.1 | Built | No | db.ts crisisLevel: number (default 4), editable dropdown in incident forms
161 | 11. Crisis Management & Emergency Recall | 11.1 Crisis Level | Level determines broadcast type/delivery channel/recipient group per FRD table | 11.1 | Not Built | No | Field is purely a stored attribute - no code branches broadcast/recall behaviour off crisisLevel value | A static DEFAULT_MATRIX reference exists in broadcast-config but is never applied at runtime
162 | 11. Crisis Management & Emergency Recall | 11.1 Crisis Level | Dynamic factors (media/reputational impact/persons involved) influence level | 11.1 | Built (manual) | No | Crisis level is a manual dropdown; mediaInvolvement fields exist separately with no automated linkage into crisisLevel | FRD only says level 'may be influenced by' - manual selection is a reasonable read; confirm automation expectation with BA
163 | 11. Crisis Management & Emergency Recall | 11.2 Crisis Recall | Triggered at Level 4+, DM reviews/confirms before dispatch | 11.2 | Not Built | No | No crisis-recall trigger/review/confirm workflow found anywhere; grep 'recall' -> zero relevant hits
164 | 11. Crisis Management & Emergency Recall | 11.2 Crisis Recall | Level 4+ recalls specific group; Level <=3 recalls broader SDC stakeholders | 11.2 | Not Built | No | No differentiated recall-group logic exists
165 | 11. Crisis Management & Emergency Recall | 11.3 Delivery Channels | SMS channel for crisis recall, with acknowledgement | 11.3 | Not Built | No | api/sms-mock/route.ts implements a full mock SMS dispatch/ack queue but is never called from any UI or other route | Ready-made mock backend exists but nothing wires a Crisis Recall UI to it - likely the next planned build increment
166 | 11. Crisis Management & Emergency Recall | 11.4 SMS Recall Workflow | Generate/queue recall SMS based on classification+group | 11.4 | Not Built | No | No caller of /api/sms-mock exists anywhere
167 | 11. Crisis Management & Emergency Recall | 11.4 SMS Recall Workflow | DM reviews/confirms queued message before dispatch | 11.4 | Not Built | No | No such UI
168 | 11. Crisis Management & Emergency Recall | 11.4 SMS Recall Workflow | Surface SMS ack status to DM | 11.4 | Not Built | No | sms-mock GET endpoint could support this in theory but nothing consumes it
169 | 11. Crisis Management & Emergency Recall | 11.5 Recall Groups | Named recall-group collections, admin CRUD, separate from Broadcast groups | 11.5 | Not Built | No | No 'recall group' admin page exists; only distribution-groups (Broadcast) exists, not a distinct Recall Group concept
170 | 11. Crisis Management & Emergency Recall | 11.5 Recall Groups | OR Analyst manages operational recall group live during active crisis | 11.5 | Not Built | No | No such role-specific operational recall management feature found
171 | 12. Reporting & Data Export | 12.1 Operational Statistics | Dedicated analytics surface: volume trends, status/type/location breakdown, processing time charts | 12.1 | Not Built | No | src/app/statistics/page.tsx is a literal placeholder: 'Coming soon - operational metrics, trend analysis, and shift reports' | Entire module is a stub
172 | 12. Reporting & Data Export | 12.1 Operational Statistics | Date range filter with presets (7d/30d/12mo/custom) | 12.1 | Not Built | No | Stub page, no filter controls
173 | 12. Reporting & Data Export | 12.1 Operational Statistics | Export from any chart/table - PDF (summaries) / CSV (bulk) | 12.1 | Not Built | No | No PDF/export library in package.json; papaparse/xlsx used only for Events bulk import
174 | 12. Reporting & Data Export | 12.1 Operational Statistics | Access/export governed by role; OR Analyst access extends to live+closed records | 12.1 | Not Built | No | N/A - module doesn't exist | OR Analyst role is only described conceptually in admin/users, no statistics surface to grant access to
175 | 12. Reporting & Data Export | 12.2 Incident Report Export | Export formal incident report as PDF, fields distinct from the entry form | 12.2 | Not Built | No | Grepped 'Export' as UI text/action across src/app and src/components - zero matches anywhere
176 | 12. Reporting & Data Export | 12.3 Case Summary Export | Export case summary (PDF/CSV) w/ linked incident, task/status summary, CMMS refs, status history, e-Diary | 12.3 | Not Built | No | No export feature found on Case detail page
177 | 12. Reporting & Data Export | 12.4 Data Export for Analytics | Bulk CSV export of incidents/cases/faults/tasks/e-Diary w/ filters (date/status/type/crisis level/location) | 12.4 | Not Built | No | No bulk export endpoint or UI found anywhere
178 | 12. Reporting & Data Export | 12.4 Data Export for Analytics | Access governed by role | 12.4 | Not Built | No | N/A - feature doesn't exist
179 | 13. System Configuration & Administration | 13.1 User/Role Mgmt | Create/edit/deactivate/reactivate user accounts | 13.1 | Built | No | admin/users/page.tsx full CRUD + status toggle, src/lib/users.ts | Persisted via localStorage, not a server DB - flag for BA/tech lead re production readiness
180 | 13. System Configuration & Administration | 13.1 User/Role Mgmt | Role assignment per Section 3 structure | 13.1 | Built | No | admin/users formRole dropdown maps to role list; admin/roles defines role/module matrix
181 | 13. System Configuration & Administration | 13.1 User/Role Mgmt | Default role-based group assignment + per-request exceptions | 13.1 | Unclear / Needs BA Confirmation | No | Only single-role-per-user model observed; no distinct 'access exception' mechanism separate from editing the role itself
182 | 13. System Configuration & Administration | 13.1 User/Role Mgmt | WOG SSO partial auto-provisioning from AD attributes | 13.1 | Not Built | No | admin/users has a manual 'WOG SSO / Non-SSO' dropdown tag only - no actual SSO/AD integration code
183 | 13. System Configuration & Administration | 13.1 User/Role Mgmt | Manual role assignment for accounts needing more than default | 13.1 | Built | No | Same manual CRUD covers this by construction
184 | 13. System Configuration & Administration | 13.1(f) DM Elevation Grant | Grant DM elevation to a named IOH user for a defined shift period | 13.1 | Partially Built | No | Sidebar.tsx has only a self-service on/off toggle for the current Duty Officer | No admin-side 'grant to named user for a defined shift' workflow, no shift-period data model
185 | 13. System Configuration & Administration | 13.1(g) Grace Period | Configure grace period after shift end before elevation auto-removed | 13.1 | Not Built | No | No grace-period config found in admin/system-settings (only Auto-Save Interval and Record Lock Timeout exist there)
186 | 13. System Configuration & Administration | 13.2 Reference Data | Incident Type/Sub-type taxonomy | 13.2 | Built | No | admin/taxonomy/page.tsx full CRUD w/ audit logging
187 | 13. System Configuration & Administration | 13.2 Reference Data | Fault Type/Sub-type taxonomy | 13.2 | Built | No | Same taxonomy page, Fault tab
188 | 13. System Configuration & Administration | 13.2 Reference Data | Location hierarchy (Road/Building/Level/Space) | 13.2 | Built | No | admin/location-hierarchy/page.tsx
189 | 13. System Configuration & Administration | 13.2 Reference Data | Task priority levels | 13.2 | Built | No | Taxonomy Priority tab, consumed via getTaskPriorityTaxonomy() in task-templates
190 | 13. System Configuration & Administration | 13.2 Reference Data | e-Diary Type/Sub-type taxonomy | 13.2 | Partially Built | No | Taxonomy eDiary tab exists | Actual e-Diary create form uses a separate hard-coded TOPICS array, not this taxonomy config - a disconnect between admin config and the live form
191 | 13. System Configuration & Administration | 13.2 Reference Data | Auto-save interval config (Sys Admin Configure / Current Ops View-only) | 13.2 | Partially Built | No | admin/system-settings configurable | No role-based Configure-vs-View-only distinction implemented - any admin visitor can edit
192 | 13. System Configuration & Administration | 13.2 Reference Data | Record lock timeout config | 13.2 | Partially Built | No | Same page, same caveat | No Current-Ops-Admin view-only restriction coded
193 | 13. System Configuration & Administration | 13.2 Reference Data | Task checklist templates | 13.2 | Built | No | admin/task-templates/page.tsx + src/lib/checklistTemplates.ts
194 | 13. System Configuration & Administration | 13.2 Reference Data | Action prompt rules (trigger conditions, recipient roles, prompt text) configurable | 13.2 | Not Built | No | No admin config page/data model for notification/prompt trigger rules - all thresholds (12/14 days, 45 min) are hard-coded in page logic
195 | 13. System Configuration & Administration | 13.2 Reference Data | DM elevation grace period config | 13.2 | Not Built | No | Confirmed absent (duplicate of 13.1(g))
196 | 13. System Configuration & Administration | 13.3 Broadcast Config | Distribution groups CRUD | 13.3 | Built | No | admin/distribution-groups/page.tsx
197 | 13. System Configuration & Administration | 13.3 Broadcast Config | Broadcast routing matrix (type/subtype/crisis level -> group/channel) | 13.3 | Built (config only, not consumed) | No | admin/broadcast-config Matrix tab, DEFAULT_MATRIX | Never consumed at runtime - no dispatch flow reads this matrix
198 | 13. System Configuration & Administration | 13.3 Broadcast Config | Broadcast templates (default field sets by type/subtype/crisis level) | 13.3 | Built (config only, not consumed) | No | admin/broadcast-config Templates tab | Not consumed at dispatch time
199 | 13. System Configuration & Administration | 13.3 Broadcast Config | End-of-day broadcast timing config | 13.3 | Not Built | No | No 'end-of-day'/EOD timing setting found (only the template category name exists)
200 | 13. System Configuration & Administration | 13.3 Broadcast Config | Broadcast action prompt rules | 13.3 | Not Built | No | No such config found
201 | 13. System Configuration & Administration | 13.4 Recall Config | Recall groups/members CRUD | 13.4 | Not Built | No | No /admin/recall-groups or equivalent page exists
202 | 13. System Configuration & Administration | 13.4 Recall Config | Recall routing rules | 13.4 | Not Built | No | None found
203 | 13. System Configuration & Administration | 13.4 Recall Config | Recall message templates | 13.4 | Not Built | No | None found
204 | 13. System Configuration & Administration | 13.4 Recall Config | Recall messaging service (SMS gateway) settings | 13.4 | Not Built | No | sms-mock is a static in-memory mock with no configurable connection settings; no admin UI for gateway config
205 | 13. System Configuration & Administration | 13.4 Recall Config | Recall acknowledgement/escalation rules | 13.4 | Not Built | No | None found
206 | 13. System Configuration & Administration | 13.5 Audit Log | All user actions/config changes/system events captured automatically | 13.5 | Partially Built | No | api/admin/audit/route.ts works, wired into: broadcast-config, distribution-groups, location-hierarchy, roles, routing-matrix, system-settings, task-templates, taxonomy, users | NOT wired into any operational action: incident creation/closure, case creation, task assignment, NOP approval, fault ticket creation, e-Diary creation, role elevation grant - significant coverage gap vs 'all user actions'
207 | 13. System Configuration & Administration | 13.5 Audit Log | Accessible to Sys Admin and Current Ops Admin only | 13.5 | Partially Built | No | admin/audit-log/page.tsx wrapped in AdminGuard | Did not verify AdminGuard's exact role list restricts to only these two roles vs broader admin access - recommend explicit check
208 | 13. System Configuration & Administration | 13.5 Audit Log | Filter by user, action type, date, record reference | 13.5 | Partially Built | No | audit-log/page.tsx has start/end date, user, module, action filters | 'Record reference' filter (by Incident/Case ID specifically) not clearly present
209 | 13. System Configuration & Administration | 13.5 Audit Log | Immutable, retained per data retention policy | 13.5 | Partially Built | No | api/admin/audit only exposes GET/POST (no PATCH/DELETE) - structurally immutable via API surface | No explicit data-retention/archival policy implementation (duration, purge job) - likely deferred to NFR 14.7
210 | 13. System Configuration & Administration | 13.5(e) Audit Log | Record DM elevation grant/expiry/removal, endorsement submit/resubmit/override reason, DM return reason, closure endorsement events | 13.5 | Not Built | No | None of these event types are ever posted to /api/admin/audit; elevation toggle has zero audit trail; incident close/return/endorsement actions only write to the incident's own log array, never the system Audit Log | Most concrete FRD-cited gap in this section - the exact events FRD calls mandatory are absent from the audit trail
211 | 14. Non-Functional Requirements | 14.1 Availability | Availability targets/SLA | 14.1 | Unclear / Needs BA Confirmation | No | FRD page 79 shows only the section heading, zero body content before jumping to Section 15 | ENTIRE NFR SECTION IS BLANK IN THE SOURCE FRD - authoring gap, not a code gap. Needs BA to author content before any Built/Not-Built verdict is possible
212 | 14. Non-Functional Requirements | 14.2 Performance | Performance targets (response time, throughput) | 14.2 | Unclear / Needs BA Confirmation | No | Same - no FRD content
213 | 14. Non-Functional Requirements | 14.3 Concurrent Users | Concurrent user targets | 14.3 | Unclear / Needs BA Confirmation | No | Same - no FRD content
214 | 14. Non-Functional Requirements | 14.4 Security | Security requirements | 14.4 | Unclear / Needs BA Confirmation | No | Same - no FRD content. For reference: no rate limiting, CSRF tokens, or input-sanitization middleware found in any API route
215 | 14. Non-Functional Requirements | 14.5 Session Management | Session timeout / idle logout | 14.5 | Not Built | No | grep 'session.*timeout' -> zero matches; consistent with no real auth session existing at all | No FRD spec exists to hold this to, but noting as functionally absent
216 | 14. Non-Functional Requirements | 14.6 Audit and Compliance | Audit/compliance requirements | 14.6 | Built (informational) | No | api/admin/audit + admin/audit-log/page.tsx + AuditLog model capture user/action/module/details/before-after snapshot/correlationId/IP | No FRD text to measure against; this verdict is against the internal Audit_Log_Types_Definition.md planning doc, not the FRD itself - confirm coverage is what's wanted
217 | 14. Non-Functional Requirements | 14.7 Data Retention and Archival | Retention/archival policy | 14.7 | Unclear / Needs BA Confirmation | No | Same - no FRD content; no archival/purge job found (the cron/generate route only generates recurring task occurrences)

## Open Items - Need Shinfeng
# | Module | Open Item | FRD Ref | Why It's Open | Suggested Question for Shinfeng | Resolved?
FRD's own explicitly-flagged Open Items (Section 15)
1 | UCS | Full list of CMS widgets/items to be embedded on the UCS dashboard is still under discussion with SDC. | 15.1 | Explicitly marked open in FRD itself | What is the final/confirmed list of CMS widgets to embed on the UCS Dashboard? | No
2 | Incident | Finalised Incident Type and Sub-type taxonomy to be confirmed. | 15.2 | Explicitly marked open in FRD itself; Appendix 16.1 lists a taxonomy but FRD flags it as provisional | Is the Appendix 16.1 Incident Type/Sub-type list final, or are further changes expected? | No
3 | Broadcast | Broadcast template content per incident type and crisis level to be confirmed. | 15.3 | Explicitly marked open in FRD itself | What is the final broadcast template content per incident type / crisis level combination? | No
4 | Broadcast | Broadcast timing rules and criteria governing which active incidents are surfaced in the interim broadcast queue are to be determined. | 15.3 | Explicitly marked open in FRD itself | What are the timing rules/criteria for the End-of-Day Interim Broadcast queue? | No
5 | Broadcast | Broadcast Matrix referenced as an open item. | 15.3 / 10.6 | FRD body text itself says '[TBC - Full broadcast matrix]' | Please provide the finalised Broadcast Matrix (type/crisis level -> recipient group/channel). | No
6 | Central Rostering Module | Proposed module for managing duty rosters (IOH staff, Rangers, contractors, on-duty personnel); scope, ownership, data input method, user groups, source of truth, and CMS notification integration all remain to be confirmed. | 15.4 | Explicitly marked open/proposed in FRD itself | Is Central Rostering in scope for this phase? If so, what is the ownership/data model/integration approach? | No
Additional items found during code review that also need Shinfeng's confirmation
7 | Roles & Permissions | FRD section 3.3.4 'Events Management' role/status action matrix heading exists but the table itself is blank in the source PDF (jumps straight from heading to section 3.4). | 3.3.4 | FRD authoring gap - no table to build against | Please provide the full Events Management role/status action matrix (who can create/edit/approve/delete Events by role and status). | No
8 | Non-Functional Requirements | Entire Section 14 (Availability, Performance, Concurrent Users, Security, Session Management, Audit/Compliance, Data Retention) contains only headings with zero body content. | 14.1-14.7 | FRD authoring gap - no NFR requirements documented anywhere | Please author the actual NFR targets/requirements for 14.1 through 14.7 (or confirm which existing document supersedes this section). | No
9 | Incident Closure | Section 5.10.1(h)/(i) separation-of-duties rule (DM cannot endorse closure of an incident they created/submitted/resubmitted themselves, even while elevated) is not implemented in code at all. | 5.10.1 | High-priority compliance control gap, not a spec ambiguity - flagging for BA awareness/prioritisation | Confirm priority/timeline for building the separation-of-duties enforcement, and whether 'actor identity' should be tracked via a new submittedBy/resubmittedBy field. | No
10 | e-Diary | Code makes e-Diary entries fully immutable (no edit, no delete for any role, citing an internal comment referencing 'FRD Section 8.2'), which is the OPPOSITE of FRD 9.1(c) which requires entries to be editable with tracked amendments and deletion restricted to System Administrator only. | 9.1(c) | Direct contradiction between current code behaviour and FRD text - needs explicit resolution | Confirm the intended e-Diary mutability model: should entries be editable with amendment tracking (per FRD 9.1c), or permanently immutable (per current code)? | No
11 | Broadcast | No Controller-facing compose/confirm/dispatch UI exists anywhere - Closure Broadcasts auto-queue to 'Pending' status on incident close but can never actually be dispatched through the app. /broadcasts page is a literal 'Coming soon' stub. | 5.11.1 / 10.1 / 10.9 | Core Broadcast dispatch workflow appears entirely unbuilt despite supporting config/data-model pieces existing | Confirm Broadcast dispatch (compose/review/send) is planned for a specific upcoming phase, and get prioritisation relative to other gaps. | No
12 | Crisis Management | Crisis Recall (entire Section 11) is essentially unbuilt - an orphaned SMS mock endpoint exists but nothing calls it; no Recall Groups, no recall routing/config, no DM review-and-confirm workflow. | 11.1-11.5 | Entire module absent - confirm scope/priority for this phase | Is Crisis Recall in scope for the current build phase? If so, what SMS gateway/provider should the mock be replaced with? | No
13 | Reporting & Data Export | Entire Section 12 (Operational Statistics, Incident/Case export, Analytics export) is unbuilt - /statistics is a 'Coming soon' stub and there is no PDF/CSV export feature anywhere in the app. | 12.1-12.4 | Entire module absent - confirm scope/priority for this phase | Confirm priority/timeline for Reporting & Data Export, and whether PDF export or CSV-only is the minimum viable requirement. | No
14 | Authentication | No real authentication exists - RoleContext is a client-side, localStorage-persisted role switcher usable by anyone with the URL. WOG SSO, 2FA, and access-denial for unauthorised accounts are entirely unbuilt. | 2.3.1 | Foundational security gap - confirm this is accepted as a prototype-phase limitation | Confirm whether WOG SSO integration is planned before go-live, and what the target timeline/owner is (likely an infra/platform-team dependency, not pure CMS-team scope). | No
15 | Dashboard / Map | '2D Island Map' runs on Leaflet + OpenStreetMap/CartoDB tiles, not OneMap as specified; only a cosmetic UI label says 'OneMap API Layout'. No geocoding, no Faults layer, no NOP boundary layer, no pin clustering. | 2.4.4 | Named integration (OneMap) does not exist in code at all - a material gap from the named requirement | Confirm whether OneMap API integration (incl. geocoding) is still required, or whether the current OSM/Leaflet map is an accepted substitute. | No
16 | Roles & Permissions | The Admin > Roles permission matrix (admin/roles/page.tsx) is a fully built, nice-looking UI but is not read by any other part of the app - actual permission gating elsewhere is hardcoded per-page. Editing the matrix has no functional effect. | 3.1 / 3.3 | Risk that stakeholders believe editing this screen changes real permissions when it does not | Confirm whether wiring the Roles matrix into live permission checks is planned, or whether hardcoded per-page gating is the accepted long-term approach. | No
17 | Duty Manager Elevation | Section 3.2 elevation model (admin-granted, shift-boxed, grace-period auto-expiring, applies to Controller too per v0.5) is not implemented - only a self-service, non-persisted Duty-Officer-only toggle exists in the sidebar. | 3.2 | Large v0.4->v0.5 behavioural change with zero implementation and no data model | Confirm priority/timeline for building the full Duty Manager Elevation workflow (admin grant, shift dates, grace period, Controller eligibility). | No
18 | Missing Roles | Zone/Contract Manager (Non-IFM), NOP Applicant (SDC Term-Contractor), and NOP Approver (SDC Term-Contractor) roles from FRD 3.1 do not exist anywhere in the switchable role model. | 3.1 | Roles referenced in FRD's own role table have no corresponding code representation | Confirm whether these 3 roles are still required for the current build phase, and their exact permission scope. | No
19 | Data Persistence | Several admin config surfaces (Users, Roles, Distribution Groups, Broadcast Config/Matrix/Templates, Taxonomy) persist to browser localStorage rather than a shared server database - changes don't propagate across users/sessions. | 13.1-13.4 (cross-cutting) | Material architecture gap for any real multi-admin/production deployment | Confirm whether backend/shared-DB persistence for admin configuration is planned before go-live, and get it prioritised/sequenced with the tech lead. | No